## Week
LAMPS-TPC software development | [20 empty] | Schedule
|  | Start Week | 2014-08-18
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Starting | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29 | Notes
| 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 2014-09-29 | 2014-10-06 | 2014-10-13 | 2014-10-20 | 2014-10-27 | 2014-11-03 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29
Phase | 2014-08-18: TPC Gometry handling
One | 2014-09-01: Particle transportation
& hit generation using
Geant4
Phase | 2014-09-15: Drift, Avalanche,
Two | 2014-09-15: Pad response, Digitization
Raw data, Clusterization
Test with beam test/cosmic data
Phase | 2014-10-20: Rieman tracking
Three | 2014-11-10: Tracking with Kaman filter
PID
Find tuning and test
Test with beam test/cosmic data
Continous | 2014-10-06: Event display
Development | 2014-10-06: Data base

## Month
Project Title | [24 empty] | Project Schedule
© 2014 Vertex42 LLC
|  | Start Date | 2014-01-01 | [22 empty] | ← Enter the project start date
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  | Project Schedule Template
| 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | Notes
| 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01
Phase
One
Phase
Two
Phase
Three

## Sample
Project Title | [20 empty] | Project Schedule
© 2014 Vertex42 LLC
|  | Start Week | 2014-01-05 | [18 empty] | ← Enter the project start date
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | Project Schedule Template
Starting | 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18 | Notes
| 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18
Phase | 2014-01-05: Quality Assurance Plan; 2014-05-18: P R O J E C T E N D
One | 2014-01-12: Project Plan
Plan Review
Phase | 2014-01-26: Draft Requrements
Two | 2014-01-26: Capacity Planning
Project Test Plan
Acceptance Test Plan
Final Requirements Specifications
Phase Review and Approval
Phase | 2014-02-16: Milestone: additional funds; 2014-02-23: Draft Design Specifications
Three | 2014-02-23: Configuration Management Plan
Architectue Design Plan
Define Interface Requirements
Shared Component Design
Integration Test Plan
Define Project Guidelines
Final Design Specifications
Phase Review and Approval

## Help
HELP
http://www.vertex42.com/ExcelTemplates/project-schedule-template.html |  | © 2014 Vertex42 LLC
About this Template
This project schedule can be used to create a basic timeline for your project.
Try the Vertex42 Gantt Chart Template if you want to something more automated for creating and managing your project schedule. (See the reference below).
How to use this Template
1) | Enter your project start date in cell E3. This will automatically update the dates in rows 6 and 7.
2) | Add tasks: Choose what phase (row) and week (column) the task will start and enter the task title into that cell. Then fill in the background color of the cells to indicate how long the task will take to complete.
If you would like to show the completion status of a task, you can fill the background with a darker or different color (see the Sample worksheet for an example).
3) | Add a milestone: If you'd like to show a milestone, you can create a vertical "line" in the schedule by changing the cell borders and the background fill (see the Sample worksheet).
Note: In the sample worksheet, the Project End milestone was created by merging cells, turning on Wrap Text, and pressing Alt+Enter after each letter to force each letter onto a new line.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Project Schedule Template
By Vertex42.com
http://www.vertex42.com/ExcelTemplates/project-schedule-template.html
© 2014 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is considered a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.