## Slide 1
Overview of The Rare Isotope Science Project
(RISP)
Myeun Kwon

## Slide 2
사업 개요 및 내용
01
사업 일반현황
1. 일반현황
사업개요 및 내용
CONTENTS
PART 1. Project Overview
PART 2. Construction Status
PART 3. System Installation
PART 4. Summary & Outlook

## Slide 3
Part 1.
Project Overview

## Slide 4: Rare Isotope Science Project (RISP)
Providing high intensity RI beams by ISOL and IF
ISOL: direct fission of 238U by 70 MeV proton
IF: 200 MeV/u 238U (intensity: 8.3 pμA)
Providing high quality neutron-rich beams
e.g., 132Sn with up to 250 MeV/u,
up to 109 particles per second
Providing More exotic RI beam
production by combination of ISOL and IF
1. Overview
Budget: KRW 1,498 billion (US$ 1.23 billion, 1$=1,209krw)
- accelerators and experimental apparatus : 502.8 billion won
- civil engineering & conventional facilities : 996 billion won (incl. site 357 billion won)
Period: 2011.12 ~ 2021.12
Goal: To build a heavy ion accelerator complex RAON,
for rare isotope science research in Korea.
* RAON - Rare isotope Accelerator complex for ON-line experiments
Construction of research and support facility to ensure the stable operation of the heavy-ion accelerator, experiment systems, and to establish a comfortable research environment
※ Accelerator and experiment buildings, support facility, administrative buildings, and guest house, etc.
Development, installation, and commissioning of the accelerator systems that provides high-energy (200MeV/u) and high-power (400kW) heavy-ion beam
System Installation Project
Facility Construction Project

## Slide 5: RAON Layout
IF System
BIS
μSR
HPMMS/
CLS
SCL2
ISOL System
LAMPS
Cyclotron
SCL3
SCL1
ECR IS
KOBRA
NDPS
Control
Center
Utility
HRS
SCL1 has been decided to postpone
: SCL3 is going to be taking a role of SCL1 in the early operation
1. Overview

## Slide 6
RAON will provide access to unexplored regions of the nuclear chart
KOBRA
IF
ISOL
ISOL+IF
1. Overview
RIBs at RAON
“More exotic, more intense, more various RIBs”

## Slide 7
Project History
1. Overview
System Installation
Facility Construction
Project General
2012
2013
2014
2015
2016
2017
Jan 2012 Established Master Plan for RISP
June 2013 Completed Technical Design
Report (TDR)
Sep 2013 Revised the Master Plan (1st)
(period extension (~2019),
implementation schedule
change, etc.)
Dec 2014 Began the basic design of facility
construction
April 2015 Revised the Master Plan (2nd)
(period extension (~2021),
implementation strategy
change, etc.)
Dec 2015 Completed the basic design
of facility construction
June 2016 Constructed the
SRF test facility
at Munji
Sep 2017 Began the facility
construction
Oct 2017 Successfully completed the
SCL demo runs
Dec 2017 Project review by TF
Feb 2011
Completed the Heavy-ion
Accelerator Conceptual Design
Dec 2011
Launched the Heavy-in
Accelerator Project
2018
March 2018
Completed
the SCL3 HWR
prototype module
performance test
2018
2019
May 2019 Revised the Master Plan (3rd)

## Slide 8
2014
2015
2016
2017
2018
2019
2020
2021
SCL demo beam
(Dec 2017)
D-1
Experiment
(Jan 2021)
18.5MeV/u
SI beam
(Dec 2020)
SCL2
(Dec 2021)
ECR-IS beam &
ISOL beam (SI beam)
(Dec 2015)
RFQ beam
(Dec 2016)
System Installation
18.5MeV/u
RI beam
(Sep 2021)
SCL
installation
(April 2019)
ISOL
Commissioning
(July 2020)
Supply of utilities
(Dec 2018)
2014
2015
2016
2017
2018
2019
2020
2021
Completion of detail design
(June 2017)
Completion of construction
(Aug 2020)
Completion of inspection of the radiation facility
(Dec 2021)
Completion of basic design
(Dec 2015)
Beginning of priority
construction
(Feb 2017)
Beginning of construction
(Sep 2017)
Building
Permit
(April 2021)
Facility Construction
(2018)
SCL3 manufacturing
SCL2 Prototype
(2019)
SCL3 Installation
SCL2 manufacturing
(2020)
SCL3 Beam Commissioning/
Const. Completion
(2021)
SCL3 Beam Commissioning/
Project Completion
Project Milestone
1. Overview

## Slide 9
Progress Rate
1. Overview
Chart: 
| End of 2011 | End of 2012 | End of 2013 | End of 2014 | End of 2015 | End of 2016 | End of 2017 | End of 2018 | End of 2019 | End of 2020 | End of 2021
Planned | 0 | 0.083 | 0.15 | 0.184 | 0.249 | 0.3046 | 0.42 | 0.6 | 0.78 | 0.91 | 1
Actual | 0 | 0.083 | 0.15 | 0.184 | 0.249 | 0.3014 | 0.407 | 0.5896
System Installation Project
As of Sept. 2019
(Planned: 72.01%,
Actual: 68.71%)
2011 2012 2013 2014 2015 2016 2017 2018 2019 2020 2021
Construction Project
Chart: 
| End of 2011 | End of 2012 | End of 2013 | End of 2014 | End of 2015 | End of 2016 | End of 2017 | End of 2018 | End of 2019 | End of 2020 | End of 2021
Planned | 0.0256 | 0.0367 | 0.1312 | 0.39 | 0.67 | 0.99 | 1
Actual | 0.0256 | 0.0367 | 0.1185 | 0.39
As of Sept. 2019
(Planned: 58.14%,
Actual: 58.14%)
2015 2016 2017 2018 2019 2020 2021

## Slide 10
Part 2.
Construction

## Slide 11
Building Layout
2. Construction
Building Layout
Assembly Bd.
SRF Test Bd.
High Energy B
IF Separator / High Energy A
HQ Office
Guest House
Info. Center
Cryogenics Bd.
ISOL
SCL
Utility Bd.
Electricity Bd.
Control Center
Low Energy A,B
Waste Strorage
Reservation
Campus Area : 952,066㎡ (including the reservation area of 144,640㎡)
Period : 2014 ~ 2021(8 years)
Cost : 996 billion won (incl. 357 billion won for land)
Building Area : 76,259㎡(11 Bds)
Total Bd. Area : 116,252㎡
Constructor : POSCO Consortium(11 companies)

## Slide 12
View of Construction Place
2. Construction
<`19.9>
<`17.01>
<`17.12>
<`18.6>
<Assembly Bd.>
<SRF Test Bd.>
<High Energy Exps.>
<ISOL>
<SCL3>
<Low Energy Exps.>
<Control Center>
View of Construction Place (`19.10)

## Slide 13
SCL3
Low Energy A/B
SCL2
IF/ High Energy A
High Energy B
ISOL
Conventional Facilities
2. Construction
Accelerator Bd.
SCL3
Bending Section
SCL3-gallery

## Slide 14
Assembly Bd.
Control Center
SRF Test Bd.
Utility Bd.
Electricity Bd.
HQ Office Bd.
2. Construction
Conventional Facilities

## Slide 15
Part 3.
System Installation

## Slide 16
Accelerator System
3. Sys. Install.
SCL3
(QWR)
SCL3
(HWR)
SCL2(SSR2)
KoBRA Beam Line
Injector
SCL2(SSR1)
Cyclotron
IF System

## Slide 17
MEBT
RFQ
LEBT
SC ECRIS
ECRIS
Accelerator System - Injector
3. Sys. Install.
∙ Two ECR ion sources on high voltage platforms
14.5 GHz ECR ion source
28 GHz superconducting ECR ion source
∙ LEBT (E = 10 keV/u)
Beam energy – 10 keV/u, Dual bending magnet
Chopper & Electrostatic quads, Instrumentation
∙ RFQ (E = 500 keV/u)
Frequency 81.25 MHz, Transmission Eff. ~98%
CW RF Power 94 kW (SSPA: 150 kW)
∙ MEBT (E = 500 keV/u)
Four RF bunchers (SSPA: 20, 15, 4×2 kW)
Simple quadrupole magnets, Instrumentation
SC ECRIS commissioning
RFQ commissioning
∙ RFQ has been conditioned to 40kW, sufficient to
accelerate A/q=4.5 beams
Output Energy of RFQ(TOF)
~508keV/u
Amplitude control of RFQ
RFQ
QWR CM
ECRIS
∙ Beam experiment for the performance enhancement
∙ Basic metal beam experiment
Ar beam experiment
Charge distribution
Ar 11+ 70uA
Injector

## Slide 18
Accelerator System – SCL3
3. Sys. Install.
SCL31(QWR)
∙ Designed performance was achieved with prototypes(2017.5)
∙ Oxygen beam was accelerated with injector and one QWR module(2017.10)
500 keV/u  ~700 keV/u, Successful long-tem operation of cryomdoule
∙ Mass production was contracted with domestic vendor(2017.12)
Pre-production cavities and cryomodules passed qualification
Thermal load <20W@6.1MV/m, 4.2 K
SCL32(HWR)
∙ Designed performance was achieved with prototypes(2017.10)
Thermal load <14.1W@6.6MV/m, 2.1 K (HWR type A)
∙ Mass production was contracted with domestic vendor(2018.5)
∙ SSPA (4kW) : 2018.07~2020.04
Prototype performance test
∙ HPRF transmission line (1-5/8”)
Installation start (2019.08)
∙ LLRF control system (2019.07~2020.06)
∙ RF reference line (81.25MHz) : ~2019.12
QWR
HWR#A
HWR#B
RF System

## Slide 19
VT target: 2.4e+8 at 6.1 MV/m
Accelerator System – QWR
3. Sys. Install.

## Slide 20
VT target: 2.3e+9 at 6.6 MV/m
Accelerator System – HWR
3. Sys. Install.

## Slide 21
CM-#2
CM-#5
 | Total (W) | Static (W) | Dynamic (W) | Q0 of cavity
QWR-CM-#1 | 11.7 | 7.7 | 4.0 | 6.0e+8
QWR-CM-#2 | 10.8 | 8.0 | 2.8 | 8.5e+8
QWR-CM-#3 | 13.1 | 8.4 | 4.7 | 5.1e+8
QWR-CM-#5 | 14.4 | 9.5 | 3.5 | 6.6e+8
All tested cryomodules meet the total thermal load requirement (20 W) though the cryomodules did not thermalized.
NO significant performance degradation of cavities during cryomodule assembly.
Accelerator System – QWR HT
3. Sys. Install.

## Slide 22
Accelerator System – SCL2
3. Sys. Install.
SCL21(SSR1)
∙ 1st prototype was manufactured by TRIUMF(2019.6)
Balloon type(less multipacting, better mechanical characteristics)
Accelerating gradient over 8.7MV/m, Multipacting below 2MV/m
∙ 2nd prototype with domestic vendor is under fabrication
Deep drawing of half shell
SCL22(SSR2)
∙ 1st prototype of cavity is under fabrication
Designed by RISP, being fabricated by domestic vendor
Balloon type, Deep drawing (depth ~280mm)
∙ 2nd prototype with IHEP is in design stage
Cylindrical type
RISP design(balloon type)
1st prototype
∙ SSPA (8, 20 kW): 2020.01~2021.06
Requirement for RF power being optimized
∙ HPRF transmission line
3-1/8”, 4-1/16” rigid coaxial
∙ LLRF control system (2020.04~2021.06)
∙ RF reference line (81.25MHz) : ~2020.12
SSR1
SSPA Prototype
RF System

## Slide 23: SCL3 Warm Section – Chamber and magnets
Diagnostic chamber
∙ 15 sets were already fabricated.
- BPMs, Wire scanners and Faraday cups
∙ Need to assemble in the clean condition
Vacuum chamber
3. Sys. Install.
∙ 53 sets were are already fabricated.
- NEG pumps and gauges
∙ Need to assemble in the clean condition
Magnets

## Slide 24
Accelerator System
3. Sys. Install.

## Slide 25
Accelerator System
3. Sys. Install.
Until September `2020

## Slide 26
Valve Box
Warm Section
QWR Cryomodule
Accelerator System-QWR unit
3. Sys. Install.

## Slide 27
Installation Procedure
3. Sys. Install.
Alignment network Survey (2019. 4 ~ )
Transportation to the accelerator building

## Slide 28
Installation Procedure
Warm section assembly
class 100
Rinse
Dry
Assemble
Leak check
Conditioning
class 10
class 100
(150℃, 120h)
3. Sys. Install.

## Slide 29
Installation Procedure
Cryomodule + Warm section
∙ Assemble in front of the tunnel (ISOL building)
∙ 15-ton crane is available.
∙ Need to connect between cryomodule and warm section in the clean condition
3. Sys. Install.

## Slide 30
Installation Procedure
Transport and positioning in the tunnel
∙ To prevent alignment change due to vibration
∙ To transport 10-ton HWR-B cryomodul in the tunnel
∙ For fine positioning
Impossible to use wheels
Adopting air caster
3. Sys. Install.

## Slide 31
Installation Procedure
Launching celebration of the 1st QWR cryomodule installation
3. Sys. Install.

## Slide 32
Installation Procedure
(Cryomodule + Warm section) + (Cryomodule + Warm section)
∙ At least one port should be assembled in the tunnel
∙ Difficult to make clean conditions due to the tight space
∙ Design a simple clean booth is underway
3. Sys. Install.

## Slide 33
Cryogenic System
3. Sys. Install.
Tasks | 2019 |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 
 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1
SCL3 Cryoplant (4.2 kW) SCL2 Cryoplant (13.4 kW) Cryogenic Distribution System (SCL3) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fabrication (QWR)
Installation and Inspection
Installation (transfer line)
Installation (valve boxes)
Fabrication
(HWR and end box)
Commissioning
Inspection
Design and Fabrication
Installation & Inspection
Now
Prototype test
SCL3 Cold Box (95 ton)
SCL2 Cold Box (130 ton)
QWR Valve Box
SCL3 Commissioning
19.5 m
15 m
Connection ( Valve Box – Cryomodule )

## Slide 34
Control System
3. Sys. Install.
Control Center
15m
Display Wall
Data Storage System
Local Control System
SCL3 Control System
Embedded EPICS IOC Controller
Beam Diagnostics Control System
Integrated Control System
Timing System
Fast Protection System

## Slide 35
RI & Experimental System
3. Sys. Install.
Low Energy Exp. Bldg
Ultra-low Exp. Bldg
High Energy Exp. Bldg
CLS
HPMMS
Neutron Facility
KOBRA
mSR
LAMPS
ISOL
IF
Bio-medical facility

## Slide 36
ISOL system
3. Sys. Install.
Line 2
Line 1
Bunker-L
Bunker-R
TIS-L
TIS-R
pre-mass separator room L
pre-mass separator room R
RFQ-c/b + EBIS
A/Q separator line
MMS
Branch point
HRMS
TIS.L Pre-sep  HRMS  user
TIS.R Pre-sep.  Mass sep.  HRMS  user
TIS Pre-sep.  HRMS  EBIS  a/qpost acc.
Test Facil. (low pow., non U)  Pre-sep  user
Now concentrating on the shortest line
TIS.L  Pre.sep  EBIS  A/q  Post.acc
ISOL building ready by ‘19.12
- Ground floor: TIS, beamline,
experimental hall
- 1st floor: experimental hall, Laboratory, utilities
- 2nd floor: Control room, Analysis room
Early stage operation

## Slide 37
IF system
3. Sys. Install.
In-Flight separator layout

## Slide 38
Nuclear science - KOBRA, LAMPS, NDPS, MMS, CLS (based on atomic physics)
Applied science - mSR (Material science), BIS (Bio & Medical application)
7 (at the beginning of RAON operation) + upgrade + a (in the future, space reserved)
3. Sys. Install.
Layout of Experimental System at RAON

## Slide 39
1. KOBRA
(KOrea Broad acceptance Recoil spectrometer & Apparatus)
2. LAMPS
(Large Acceptance Multi-Purpose Spectrometer)
∙ Research Studies of nuclear structure and nuclear
astrophysics in the energy range of < a few tens of MeV/u
∙ Current status Under fabrication (start installation from Sep. 2019)
∙ Research Studies of nuclear matter and nuclear reactions
with stable and RI beams at intermediate energy regime
∙ Current status Under fabrication (start installation from Jan. 2021)
IF separator
3. ACC. & Exp.
3. Sys. Install.
Current Status of Experimental System

## Slide 40
3. MMS (Mass Measurement System)
∙ Research High precision mass measurement of
short lived rare isotopes
∙ Current status Under assembly and test
(start installation from Feb. 2020)
MR-TOF-MS
4. CLS (Collinear Laser Spectrometer)
∙ Research Model independent Studies of
nuclear ground and isomeric state properties
∙ Current status Restart development
(start installation from Jan. 2020)
5. NDPS (Neutron Data Production System)
∙ Research Measurement of neutron
induced reaction data for nuclear science
∙ Current status Restart development
6. mSR (Muon Spin Rotation/Relaxation/Resonance )
∙ Research Studies of local electromagnetic structures and
exotic properties of material by using polarized muons
∙ Current status Restart development
7. BIS (Beam Irradiation System)
∙ Research Biomedical studies such as cancer treatment,
human body effect by space radiation and cell mutation
∙ Current status Restart development
(start installation from Jan. 2021)
(start installation from Nov. 2020)
(start installation from Feb. 2021)
3. ACC. & Exp.
3. Sys. Install.
Current Status of Experimental System

## Slide 41: Scientific program at early phase operation(candidate)
Facility | Subject for early phase operation
KOBRA | ∙ Transfer reaction measurements in inverse kinematics (29P(d,p)30P, 26Al(a,p)24Si) ∙ Radiative capture reactions using batch mode RI beams (26gAl(p,g)27Si) ∙ RI beam production via quasi-projectile-like fragmentation for 16O or 40Ar
LAMPS | ∙ Ar+KCl or Xe+CsI in case of IF separator commissioning not completed
MMS | ∙ Isomer separation with using 26g.s.Al and 26mAl beams
CLS | ∙ Laser ionization and measurement of isomeric property for 26Al
NDPS | ∙ Activation experiments with a quasi mono energy neutrons for light and heavy nuclei ∙ Surrogate reactions for fission
mSR | ∙ One of research areas of superconductivity and quantum magnetism with their scientific significance at the time of the μSR instrument completion
BIS | ∙ Physical dose distribution and linear energy transfer measurements with a 12C+6 beam (310 MeV/u)
3. Sys. Install.

## Slide 42
International Cooperation (MOUs with 18 Intl Institutes)
3. Sys. Install.
27

## Slide 43
Part 4.
Summary & Outlook

## Slide 44
Accelerator
Mass production for SCL3 is under way
SCL2 is under pre-production phase
From April, 2019, installation for SCL3 has been started
By the end of 2021, we will achieve
SI beams: Stable ion beams (16O, 40Ar) from ECRIS  SCL3  low E exp hall
RI beams: RIBs extraction from ISOL  re-acceleration through SLC3  low E exp hall
Stable / RI beams will be delivered to low-E experimental hall
Early phase experiments are going to be performed using KOBRA
  RIBs production at KOBRA (A<~50, beam energy < 20 MeV/u) using SI beams from SCL3
Beam commissioning starts for SCL2
Installation and commissioning for IF, LAMPS, Neutron, bio-medical and muSR
   Collaborative works with RUA (RAON Users Association) via RULC (RAON Users Liason Center)
Post RISP (2021 ~ )
Beam acceleration for ISOL  SCL3  SCL2  IF (ISOL+IF)
Beam commissioning and experiments for IF, LAMPS, Neutron, bio-medical and muSR
Ramping-up to get the 400kW beams (more than 5 yrs)
Energy upgrade to 400MeV/u (requires budget)
Summary & Outlook
4. Summary

## Slide 45
Thank you